Meeting Minutes

| Location: | MS Teams |
| --- | --- |
| Date: | 03/09/2026 |
| Time: Chairperson: Minute Taker: | 21:00 Peng Song Peng Song |
| Absent with apology: | None |
| Absent without apology: | None |

Progress made since the last meeting

| No | Item | Responsible Person/s | Status/Issues/Remarks |
| --- | --- | --- | --- |
| 1 | Checked completion of Meeting 2 action items | All members | Completed - all action items planned before Meeting 3 were completed. The cleaned shared data is ready on GitHub, all four members completed their Python analysis, GitHub and the task board were updated, the PPT preparation was started, and the AI form was prepared. |
| 2 | Checked the final results for the four analysis tasks | All members | Completed - checked Sihao's fouls analysis, Luke's assists-per-90 analysis, Peng's UEFA possession analysis and Abel's goalkeeper analysis. Each person reviewed their main graph, 95% CI, t-test result and limitation. The main statistical assumptions and data-cleaning decisions were also discussed. |
| 3 | Confirmed graphs, slide structure and speaking order | All members | Completed - confirmed the speaking order as Peng, Sihao, Luke and Abel. Slides will use the same simple style with key results, clear graphs and short result tables. Large code screenshots will not be used. |
| 4 | Confirmed recording rules and timing | All members | Completed - each member will keep their part under 3 minutes, show their CDU student ID first, keep their face visible and use PowerPoint. Separate clips will be combined into one unlisted YouTube video. |
| 5 | Checked GitHub and the final submission package | All members | Completed - confirmed the repository structure and final submission files. The repository link will be checked to make sure the lecturer can access it. The final zip will contain the unlisted YouTube link, signed AI declaration and a text file with the GitHub URL. |

Next deliverables and internal deadlines

| No | Item | Responsible Person/s | Internal Deadlines |
| --- | --- | --- | --- |
| 1 | Final dataset check; fouls graph and key numbers | Sihao Cui | 04/09/2026 Before rehearsal |
| 2 | Final PowerPoint template; add and merge all slides | Luke Ren | 30/08-04/09/2026 |
| 3 | Conclusion slide; video editing/upload; AI declaration signatures | Abel Qin | 04/09/2026 07-08/09/2026 08/09/2026 |
| 4 | GitHub/task board/minutes; repository link text file; final zip package | Peng Song | Ongoing 09/09/2026 |
| 5 | Timed rehearsal; record individual clips; final Assessment 2 submission | All members | 04/09/2026 05-06/09/2026 10/09/2026 2:00 PM ACST |

Comments (if any):

In Meeting 3, we confirmed that all action items planned after Meeting 2 had been completed. We checked the final Python results for all four tasks, chose the main graphs and key results, and confirmed the presentation, recording and submission plan. This was our last formal meeting. Before submission, everyone will complete their final presentation and submission tasks, practise their part and check that all files and links work correctly.