Meeting Minutes

| Location: | MS Teams |
| --- | --- |
| Date: | 14/08/2026 |
| Time: Chairperson: Minute Taker: | 4:30 PM Peng Song Peng Song |
| Absent with apology: | None |
| Absent without apology: | None |

Progress made since the last meeting

| No | Item | Responsible Person/s | Status/Issues/Remarks |
| --- | --- | --- | --- |
| 1 | Reviewed the Assessment 2 requirements for Objective 1 | All members | Completed - confirmed we only need to do Objective 1 this time, not the regression part. Each task still needs a question, descriptive statistics, a confidence interval and a t-test. |
| 2 | Confirmed the four analysis tasks | All members | Completed - Sihao: fouls; Luke: assists per 90; Peng: UEFA possession; Abel: goalkeeper save percentage. |
| 3 | Discussed the data and methods for each task | All members | Completed - went through the sample, descriptive statistics, CI and t-test for each task, and talked about some limitations, like the data not being fully independent. |
| 4 | Agreed on the structure of the three shared datasets | Sihao / All members | Completed - agreed on three CSV files: team-match.csv, player.csv and GK-match.csv, with the main columns for each. Column names will not be changed later so no one's code breaks. |
| 5 | Started checking data sources | Sihao | In progress - Sihao is checking FIFA, FBref and The Stats Don't Lie. Goalkeeper data (saves, shots on target faced) will be checked first, so we know early if it's missing. |
| 6 | Confirmed group responsibilities and presentation plan | All members | Completed - Sihao will collect and clean the data; Peng will manage GitHub, meeting notes and final submission; Luke will prepare the PPT; Abel will handle the AI form and final video. Speaking order: Peng, Sihao, Luke, Abel. |

Next deliverables and internal deadlines

| No | Item | Responsible Person/s | Internal Deadlines |
| --- | --- | --- | --- |
| 1 | Raw data; cleaned shared dataset; fouls analysis | Sihao Cui | 23/08/2026 26/08/2026 28/08/2026 |
| 2 | Assists-per-90 analysis; PowerPoint template and slide merge | Luke Ren | 28/08/2026 30/08-02/09/2026 |
| 3 | Goalkeeper analysis; video editing/upload; AI declaration form | Abel Qin | 28/08/2026 07-08/09/2026 08/09/2026 |
| 4 | Possession analysis; GitHub/task board and meeting notes; final submission package | Peng Song | 28/08/2026 Ongoing 09/09/2026 |
| 5 | Timed rehearsal; final Assessment 2 submission | All members | 03/09/2026 10/09/2026 2:00 PM ACST |

Comments (if any):

In Meeting 1, we confirmed the four tasks, data plan, methods and deadlines. This meeting is before Checkpoint 1 (15/08/2026). Before Meeting 2, everyone will start their own work and we will check the real data and early results next time. Meeting 2 will be held before Checkpoint 2 (29/08/2026).