Meeting Minutes

| Location: | MS Teams |
| --- | --- |
| Date: | 25/08/2026 |
| Time: Chairperson: Minute Taker: | 22:45 Peng Song Peng Song |
| Absent with apology: | None |
| Absent without apology: | None |

Progress made since the last meeting

| No | Item | Responsible Person/s | Status/Issues/Remarks |
| --- | --- | --- | --- |
| 1 | Checked progress since Meeting 1 | All members | Completed - checked GitHub, shared data and early Python work. No final results were reported yet. |
| 2 | Checked shared datasets and cleaning plan | Sihao / All members | In progress - team_match.csv, player.csv and gk_match.csv are being organised. Raw and cleaned data will be kept separate, and column names will stay fixed. |
| 3 | Reviewed progress for the four analysis tasks | All members | In progress - Sihao: fouls; Luke: assists per 90; Peng: UEFA possession; Abel: goalkeeper save percentage. Each person discussed data cleaning, descriptive statistics, 95% CI, t-test and key limitations. |
| 4 | Confirmed the required Python analysis steps | All members | Completed - every task will include a question, data wrangling, data preparation and sampling, descriptive statistics, a 95% CI and a t-test. Analysis and graphs will be done in Python. |
| 5 | Checked GitHub, task board and presentation plan | All members | Completed - files will be organised in data, notebooks, slides and meeting-minutes. The task board will use To do, In progress and Done. Slides will use key results and clear graphs. |

Next deliverables and internal deadlines

| No | Item | Responsible Person/s | Internal Deadlines |
| --- | --- | --- | --- |
| 1 | Cleaned shared datasets; fouls analysis | Sihao Cui | 26/08/2026 28/08/2026 |
| 2 | Assists-per-90 analysis; 90/180/270 checks; PPT template | Luke Ren | 28/08/2026 30/08-02/09/2026 |
| 3 | Goalkeeper analysis; AI form; video editing/upload | Abel Qin | 28/08/2026 08/09/2026 07-08/09/2026 |
| 4 | Possession analysis; GitHub/task board/minutes; final package | Peng Song | 28/08/2026 Ongoing 09/09/2026 |
| 5 | Meeting 3 review; timed rehearsal; final submission | All members | Before 29/08/2026 03/09/2026 10/09/2026 2:00 PM ACST |

Comments (if any):

In Meeting 2, we checked the shared data, early Python work and progress of all four tasks. No final results were reported yet. Before Meeting 3, everyone will finish or nearly finish their analysis and bring the real Python results, at least one useful graph, the 95% confidence interval and t-test output.